APPROVED by

Order No. V-62 of the Minister of Foreign Affairs of the Republic of Lithuania of 17 April 2014

(Amended by the Order No. V- 234 of the Minister of Foreign Affairs of the Republic of Lithuania of 9 November 2015)

EMBASSY OF THE REPUBLIC OF LITHUANIA TO UKRAINE

project conception No. 4

„Sharing of good practices in the area of Energy efficiency“

March 2, 2017

| GENERAL INFORMATION ABOUT THE PROJECT |  |
| --- | --- |
| 1. Partner country | Ukraine |
| 2. Areas of cooperation | Sharing of good practices, energy efficiency |
| 3. Project description |  |
| 3.1. Aim of the project | To contribute to the improvement of the energy efficiency in Ukraine |
| 3.2. Project objectives | 1. To pass on good Lithuanian practice and expertise in the area of energy efficiency. 2. To evaluate or help in evaluating the status of energy efficiency of Ukraine’s city (-ies). 3. To implement small-scale energy efficiency project, which would serve as a practical example. |
| 3.3. Target group | Ukraine’s local authorities, energy efficiency experts, local communities |
| 4. Foreseen duration of project implementation | 2017-05-01 - 2017-11-17 |
| 5. Advantages | Experience in implementation of similar projects; Other sources of funding and/or financial contribution of the applicant |